## Backend Action Items
Endpoint / Area | Problem
GET /Api/list — singer & poet query params | Server-side filtering by singer or poet is broken / unreliable. Sending ?singer=Kabir&poet= returns the same full dataset regardless of params.
GET /Api/song_filters — poet names | /Api/song_filters does not return a reliable or complete list of poet names for the filter panel.
GET /Api/song_filters — themes | Themes returned by /Api/song_filters are absent, incomplete, or test data. /Api/poem_filters returns only 1 real theme (Saudaagir asdasdasd - a test entry).
GET /Api/song_versions | Returns HTTP 500 (Database Error) for all valid song IDs on staging. The Other Versions of this Song feature is completely broken.
GET /Api/news — draft filtering | Items with published: 0 are draft/test entries and should not be visible to the public. No frontend filtering exists — all items including drafts are displayed.
GET /Api/news — video category | News items with category: video are silently dropped because no video player is implemented. Video items are skipped without any fallback.
GET /Api/reflection_filter — format field | The format field returns incorrect or inconsistent values (e.g. wrong casing, unexpected strings). The filter panel hardcodes expected values as a fallback.
GET /Api/poems — null content fields | note_text, glossary, and english_translation_text are null for all poems on staging. NOTES and GLOSSARY buttons never appear.
GET /Api/poem_filters — test theme | Only 1 theme exists in poem filters: Saudaagir asdasdasd — clearly a test entry. The theme filter panel looks broken.
GET /Api/news — null content | news_title and ajab_news_content are null on all real news items. Real content only appears inside popup_items[].
GET /Api/explore_songs, /Api/explore_reflection, /Api/explore_person — response latency | All three detail-page endpoints take 8-12 seconds to respond on staging. The frontend shows a fullscreen loader during this wait, but the delay is severe enough to feel broken. List endpoints (/Api/list, /Api/person_list, etc.) respond in under 3 seconds — the explore_* queries are significantly heavier.
GET /Api/nitesh — endpoint naming | The search endpoint is named /Api/nitesh (a developer name). This must be renamed to a production-appropriate name (e.g. /Api/search) before public launch. The frontend references this via SEARCH_ENDPOINT in lib/utils/search.ts and will need updating once renamed.